QEP IMPLEMENTATION PLAN

| QEP IMPLEMENTATION | IMPLEMENTATION DESCRIPTION | PERSON (S) RESPONSIBLE | DEADLINE |
| --- | --- | --- | --- |
| Identify test and control groups | Faculty and staff are informed which DMA 010, 020, and 030 classes are test groups and will receive prescribed QEP interventions | Statistician and IT | Before the semester begins |
| Assess DMA 010 students for whole number proficiency | Students who score less than 80% are referred to SI | DMA faculty | Administered in first hour of DMA 010 |
| Begin Supplemental Instruction | Lead Supplemental Instructor and SI Tutors observe DMA 010, 020, and 030 courses, lead SI sessions, and enter SI data in QEP Database one hour a day each day of the week of a term (up to 15 hours) | Lead SI, SI Tutors, Lead DMA Instructor | Beginning of each term |
| Identify first-time DMA 010, 020, and 030 students | DMA 010, 020, and 030 student academic histories are reviewed to determine first- time attenders | QEP Director/CAC/ Research Coordinator | Before each term |
| Administer ENGAGE College Survey | DMA 010, 020, and 030 first-time students take the assessment | Lead Counselor and QEP Director/ CAC | During the first or second hour of scheduled course meeting |
| Report and send ENGAGE College Survey results to Director of QEP | Excel report is created reporting results of all categories from student surveys | Lead Counselor | 72 hours after last survey is administered (business week) |
| QEP IMPLEMENTATION | IMPLEMENTATION DESCRIPTION | PERSON (S) RESPONSIBLE | DEADLINE |
| Enter ENGAGE results in QEP Database | Categories Academic Self-Confidence and Study Skills are entered in the QEP Database. As results are entered, if a student’s score in one or both of these categories is 33 or below, a CAC referral will be initiated. | QEP Director/ CAC | 72 hours after ENGAGE report is delivered (business week) |
| Generate automated electronic CAC referral from ENGAGE | Database generates an email referral to the CAC; CAC then initiates contact with the student | QEP Director/CAC | Ongoing |
| Assess student participation in DMA 010, 020, and 030 for CAC referral | DMA faculty recognizes a student has psycho-social barriers impeding student success and uses Database to initiate CAC referral selecting relevant tabs and making relevant comments | DMA faculty, CAC | Ongoing |
| Generate automated electronic CAC referral from DMA faculty | Database generates an email referral to the CAC; the CAC then initiates contact with the student. If during CAC meeting it is determined an SI referral is also necessary, the CAC will initiate an SI referral. | CAC | Ongoing |
| QEP IMPLEMENTATION | IMPLEMENTATION DESCRIPTION | PERSON (S) RESPONSIBLE | DEADLINE |
| Assess student performance in DMA 010, 020, and 030 for Supplemental Instruction Referral | Students who score less than 80% on Quizzes 1 and/or 2 require an SI and/or CAC referral. As DMA faculty members input quiz scores, they will also initiate referrals. | DMA faculty | 48 hours after quiz completion (business week) |
| Generate automated electronic SI referral from DMA faculty | Database generates an email referral to the Tutorial Lab Coordinator and the student. | Tutorial Lab Coordinator | Ongoing |
| Conduct Supplemental Instruction for students | Student attends SI and data is recorded | Lead SI and SI Tutors | Ongoing |
| Review Supplemental Instruction data | Discuss DMA 010, 020, and 030 SI data | Lead SI, SI tutors, Lead DMA Instructor | Ongoing |
| Review DMA 010, 020, and 030 end-of-term data | Discuss DMA 010, 020, and 030 concerns and results | DMA faculty, LAP Director, QEP Director | 20thhour of each 4 week term |
| Review and Analyze data | Make recommendations to the administrative team | QEP Review Committee members | Ongoing |